## Summary
Concierge.AI Manual UI Checklist
Guest URL | http://127.0.0.1:8080 | [5 empty] | Overall Status
Admin URL | http://127.0.0.1:8080/admin | [5 empty] | Pass | 48
Default Username | admin | [5 empty] | Fail | 20
Default Password | ChangeMe123! | [5 empty] | Pending | 63
[7 empty] | Not Tested | 1
Instructions | Enter Pass, Fail, or Pending in the Result column and add observations in Comments. Pending means the test is intentionally deferred or waiting on a dependency; blank means not yet tested.
Section | Total | Pass | Fail | Pending | Not Tested | Completion %
Guest Experience | 28 | 7 | 0 | 20 | 1 | 25%
Admin Authentication | 8 | 6 | 0 | 2 | 0 | 75%
Admin Navigation | 36 | 22 | 12 | 2 | 0 | 94.44%
Admin Controls | 47 | 7 | 6 | 34 | 0 | 27.66%
Responsive Review | 8 | 5 | 2 | 1 | 0 | 87.5%
Environment Checks | 5 | 1 | 0 | 4 | 0 | 20%
TOTAL | 132 | 48 | 20 | 63 | 1 | 51.52%

## Guest Experience
# | Check | Expected result | Result | Comments
G01 | Open guest page | Welcome screen loads without an error | Pass | Verified in the local browser on 2026-09-22.
G02 | Hotel menu button | Side menu opens | Pass | Verified in the local browser on 2026-09-22.
G03 | Header options button | Same side menu opens | Pending
G04 | Close menu button | Side menu closes | Pass | Verified side-menu close behavior in the local browser on 2026-09-22.
G05 | New conversation | Existing messages are cleared and a new session starts | Pending
G06 | Hotel information | Hotel information appears as an assistant message | Pending
G07 | Language | Language preference changes and confirmation appears | Pending
G08 | Accessibility | Accessibility display mode toggles | Pending
G09 | Privacy | Privacy guidance appears | Pending
G10 | Help | Concierge help guidance appears | Pending
G11 | Suggested prompt buttons | Every visible prompt sends its message | Pending
G12 | Empty composer | Send button remains disabled | Pass | Verified in the local browser on 2026-09-22.
G13 | Typed composer message | Send button becomes enabled | Pass | Verified in the local browser on 2026-09-22.
G14 | Send button | User message and assistant response appear | Pass | Verified in the local browser on 2026-09-22.
G15 | Enter key | Sends the message | Pending
G16 | Shift+Enter | Adds a new line without sending | Pending
G17 | Composer width | Text field uses most of the composer; placeholder is not vertically wrapped | Pending
G18 | Breakfast question | Verified breakfast hours are returned | Pass | Verified the configured breakfast-hours answer in the local browser on 2026-09-22.
G19 | Checkout question | Verified checkout time is returned | Pending
G20 | Pool question | Verified pool hours are returned | Pending
G21 | Wi-Fi request | Enabled authentication form or guidance appears | Pending
G22 | Wi-Fi Continue with empty fields | Validation message appears | Pending
G23 | Wi-Fi valid mock credentials | Authentication succeeds in mock mode | Pending
G24 | Dining request | Recommendation cards appear | Pending
G25 | Recommendation Details | Description expands and collapses | Pending
G26 | Recommendation Directions | Configured map URL opens | Pending
G27 | Service request | Confirmation card appears | Pending
G28 | Confirm service request | Request ID is returned

## Admin Authentication
# | Check | Expected result | Result | Comments
A01 | Open /admin while signed out | Redirects to admin login | Pass
A02 | Show/Hide password | Password visibility toggles | Pass
A03 | Invalid login | Error appears and page remains on login | Pass
A04 | Forgot password | Recovery dialog opens with username copied | Pending | Email/SMTP is not yet configured, so the password-recovery workflow cannot be fully tested.
A05 | Request reset | Generic reset confirmation appears | Pending
A06 | Recovery Cancel/Close | Dialog closes | Pass
A07 | Valid login | Admin dashboard opens | Pass
A08 | Logout | Session ends and /admin redirects to login | Pass

## Admin Navigation
# | Check | Expected result | Result | Comments
N01 | Dashboard | Dashboard panel opens | Pass | Operational dashboard implemented and manually verified with property, AI, ANTlabs, session, request, and version status.
N02 | Conversations | Conversation list opens | Pass | Implemented property-scoped retention (1-365 days), active/historical clarity, and purge controls; covered by automated tests.
N03 | Guest Requests | Request workflow opens | Pass | Implemented request assignment, department, priority, notes, and close controls; covered by automated API tests and UI inspection.
N04 | Guest Sessions | Session/memory panel opens | Pass | Session view now exposes property-scoped session, stay, and device details; covered by automated tests.
N05 | Preview | Guest modules panel opens | Pass | Implemented property-scoped guest module add/edit/enable/delete/order management and guest-menu publication; round-trip covered by automated tests.
N06 | Hotel Information | Correct placeholder/status panel opens | Pass | Implemented hotel information editing/publication and dynamic guest answers from configured property data; covered by automated tests.
N07 | Rooms | Correct configuration-required panel opens | Pass | Implemented property-scoped room CRUD through hotel configuration; covered by automated round-trip tests.
N08 | Facilities | Correct coming-soon panel opens | Pass | Implemented property-scoped facility CRUD and guest-facing publication; covered by automated tests.
N09 | Restaurants | Correct coming-soon panel opens | Pass | Implemented property-scoped restaurant CRUD and guest-facing publication; covered by automated tests.
N10 | Service Catalog | Department/service editor opens | Pass | Added concise guidance for service authoring controls.
N11 | Recommendations | Recommendation editor opens | Pass | Added concise guidance for recommendation authoring controls.
N12 | Zones & Maps | Map editor opens | Fail | Map image background and Freeform drawing are implemented, but upload-to-draw persistence still needs a complete browser-runner validation.
N13 | Knowledge Overview | Knowledge panel opens | Fail | Knowledge content cannot currently be added, edited, or deleted. Add complete knowledge-management controls.
N14 | Documents | Correct coming-soon panel opens | Fail | Document management is incomplete; administrators cannot currently add, edit, or delete documents.
N15 | FAQs | Correct coming-soon panel opens | Fail | FAQ management is incomplete; administrators cannot currently add, edit, or delete FAQs.
N16 | Models & Providers | AI provider panel opens | Pass | AI provider credentials remain encrypted/masked; connection testing and model refresh are supported. Live-provider validation remains tracked in Environment Checks.
N17 | Personality | Correct coming-soon panel opens | Fail | Personality settings cannot currently be added or edited. Add configurable personality controls.
N18 | Guardrails | Correct coming-soon panel opens | Fail | Guardrail settings cannot currently be added or edited. Add configurable guardrail controls.
N19 | Improvement Loop | Loop controls open | Pass | Removed Improvement Loop from the main product navigation; legacy backend routes remain only for compatibility.
N20 | AI Usage | Correct coming-soon panel opens | Pass | AI Usage now reports property-scoped request, token, error, latency, and provider metrics; manually verified with truthful zero-state data.
N21 | PMS | Correct configuration-required panel opens | Pass | Removed PMS/Booking from the main product navigation.
N22 | ANTlabs / Wi-Fi | Correct configuration-required panel opens | Pass | Implemented truthful ANTlabs configuration status and connection testing; mock simulation was manually verified. Live gateway validation remains tracked in Environment Checks.
N23 | Webhooks | Correct coming-soon panel opens | Fail | Webhook management is not yet functional. Future enhancements should include endpoint configuration, event selection, test delivery, retry status, and delivery logs.
N24 | Design | Appearance editor and preview open | Pending | Expand the Design section with more flexible customization options so administrators can control the guest experience as much as possible, including typography, spacing, colors, layout, components, and responsive previews.
N25 | Branding / Intro | Intro editor opens | Pending | Expand Branding / Intro customization so administrators have more control over logos, imagery, welcome content, layout, typography, and presentation across devices.
N26 | Location | Location analytics panel opens | Fail | Location information cannot currently be added, edited, or deleted. Add complete location-management controls.
N27 | Users | User table opens | Pass | The password-reset flow needs an SMTP/email configuration page so administrators can configure outbound email for password-reset messages.
N28 | Roles | Role list opens | Pass
N29 | Permissions | Permission catalog opens | Pass
N30 | Domain | Configuration-required panel opens | Fail | Add complete domain configuration controls to this section.
N31 | SSL | Configuration-required panel opens | Fail | Add complete SSL certificate configuration and management controls to this section.
N32 | Network | Configuration-required panel opens | Fail | Add the required network configuration controls to this section.
N33 | Audit | Audit table opens | Pass
N34 | Security | Password and session panel opens | Pass | The functionality works, but the Security page UI needs visual cleanup and better consistency.
N35 | Settings | Correct coming-soon panel opens | Fail | Replace the placeholder with the required application settings and configuration controls.
N36 | License | License panel opens | Pass | Removed License from the main product navigation.

## Admin Controls
# | Check | Expected result | Result | Comments
C01 | Collapse/expand sidebar | Sidebar changes state and remains usable | Pass | Verified sidebar collapse and expansion in the local browser on 2026-09-22.
C02 | Profile and Account Settings | Profile panel opens | Pass
C03 | Security and Change Password menu | Security panel opens | Pending
C04 | Switch Property | Property selector receives focus | Pending
C05 | Save Draft | Draft design is saved | Pending
C06 | Publish | Guest app receives published design | Pass
C07 | Discard | Unsaved design changes are restored | Pending
C08 | Restore design version | Selected version becomes the draft | Pending
C09 | Add/remove prompt | Prompt row is added/removed and preview updates | Pending
C10 | Mobile/Tablet/Desktop preview | Preview width changes | Pass
C11 | Save AI Settings | Settings persist and success message appears | Pass
C12 | Configure provider | Provider drawer opens | Pending
C13 | Save provider | Provider configuration persists | Pending
C14 | Add/replace provider credential | Credential status updates; secret is not displayed | Pending
C15 | Remove provider credential | Credential is removed | Pending
C16 | Close provider drawer | Drawer closes | Pending
C17 | Save improvement loop | Objective and settings persist | Pass | Obsolete control intentionally removed with the Improvement Loop product surface (N19).
C18 | Loop lifecycle controls | Enabled controls change loop state appropriately | Pass | Obsolete control intentionally removed with the Improvement Loop product surface (N19).
C19 | Map Select/Rectangle/Polygon/Ellipse | Selected tool becomes active | Fail | Toolbar tools including Freeform are implemented, but the full pointer workflow still requires validation with an uploaded map.
C20 | Map Duplicate/Delete/Undo/Redo | Draft objects change correctly | Fail
C21 | Save Object | Zone/facility/AP is saved | Fail
C22 | Floor-map upload | Valid PNG/JPEG/SVG/PDF uploads | Fail
C23 | Create/Restore Stay | Stay ID appears | Fail
C24 | Save Compact Memory | Memory persists | Fail
C25 | Record Observation | Observation is accepted | Pending
C26 | Load Report | Location report appears | Pending
C27 | Save Intro | Intro settings persist | Pending
C28 | Intro asset upload | Valid supported asset uploads | Pending
C29 | Refresh conversations | Conversation list refreshes | Pending
C30 | Take Over/Return to AI | Conversation ownership toggles | Pending
C31 | Send Response | Staff response appears in conversation | Pending
C32 | Close conversation | Conversation status becomes closed | Pending
C33 | Save Department | Department appears and can be edited | Pending
C34 | Save Service | Service appears and can be edited | Pending
C35 | Duplicate/Archive/Delete service | Each action updates the service list | Pending
C36 | Create Request | Operational request appears | Pending
C37 | Advance request status | Status moves to the next workflow state | Pending
C38 | Save/Edit/Delete recommendation | Recommendation list updates correctly | Pending
C39 | Create/Edit user | User table updates correctly | Pending
C40 | Reset user password | Temporary password is accepted | Pending
C41 | Disable/Enable user | User status changes | Pending
C42 | Revoke Sessions | Confirmation appears | Pending
C43 | View Activity | Audit panel opens filtered to the user | Pending
C44 | Delete User | Confirmation appears and user is removed | Pending
C45 | Create/Edit Role | Role list updates correctly | Pending
C46 | Refresh/Apply audit filters | Audit results refresh | Pending
C47 | Change own password | Password changes without a JavaScript error | Pending

## Responsive Review
# | Check | Expected result | Result | Comments
R01 | Guest desktop | No clipping, overlap, or horizontal scrollbar | Fail | Review all guest and admin tabs for layout issues. Overlapping UI elements were observed on multiple screens.
R02 | Guest mobile | Header, prompts, composer, and send button remain usable | Fail | The upload button is not functioning on mobile.
R03 | Admin desktop | Sidebar, top bar, forms, dialogs, and drawers fit correctly | Pass | Collapsible desktop/tablet sidebar and mobile overlay drawer are implemented; desktop collapse was manually verified on 2026-09-22.
R04 | Admin tablet | No horizontal page overflow | Pass | Collapsible desktop/tablet sidebar and mobile overlay drawer are implemented; desktop expansion was manually verified on 2026-09-22.
R05 | Admin mobile | Every navigation item is reachable | Pass | Collapsible desktop/tablet sidebar and mobile overlay drawer are implemented; desktop behavior was manually verified on 2026-09-22.
R06 | Keyboard navigation | Focus indicator is visible and order is logical | Pass
R07 | Dialog keyboard behavior | Tab remains usable; Escape/Close works | Pass
R08 | Dark mode | Guest page remains readable | Pending

## Environment Checks
# | Check | Expected result | Result | Comments | Note
E01 | Test AI provider connection | Successful connection and latency appear | Pass |  | These checks require valid staging credentials or connected services.
E02 | Refresh provider models | Live provider models populate | Pending | Requires valid external AI-provider credentials and a live model-refresh check.
E03 | Run improvement-loop iteration | Provider returns an iteration for review | Pending | Improvement Loop was intentionally removed from the main product; legacy compatibility routes were not part of this production-scope validation.
E04 | ANTlabs live authentication | Gateway accepts valid guest credentials | Pending | Requires access to a live ANTlabs gateway; mock simulation and truthful status reporting were verified.
E05 | Production upload storage | Uploaded files remain available after restart | Pending | Requires production-storage restart and persistence verification.